## Operational Calendar
School Safety Program Operational Calendar
The operational calendar is a fluid document that should be used by the school administrator, officer or counselor or social worker, and the School Safety Assessment and Prevention Team to monitor program implementation and provide continuous improvement throughout the school year. *Asterixed items are requirements for the grant
District:
School(s):
School Administrator Name(s):
Officer, Counselor or Social Worker Name:
Project Activities/Milestones | Responsible Personnel | School Year: | [11 empty] | Completed
|  | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Yes | No | Comments
*SSP Training (L100-L500, NOT, New CSW, LRE) | SRO, CSW, Site Admin, District Admin | [14 empty] | SSP University Course Catalog
FY23 SSP Training Schedule
*Establish SSAPT / First SSAPT Meeting / Roll-out to Staff, Students, and Parents / Operational Calendar / Intervention Matrix | SRO, CSW, Site Admin, School prevention coordinator or school mental/behavioral health expert, or similar role, PBIS team (if applicable) |  | X
SSAPT Agenda
SSP FY23 Requirements & Guidance, pages 1-2
SSP Guidance Manual, Checklists for SSP Members,pages 46-51
SSAPT Data Analysis Activity
*SSAPT Meetings / Needs Assessments | SRO, CSW, Site Admin, School prevention coordinator or school mental/behavioral health expert, or similar role, PBIS team (if applicable), |  | X | X | X | X | X | X | X | X | X | X |  |  |  | Guidance Manual, page 6.
SSAPT Data Analysis Activity
*Law Related Eduction (LRE)/Social Emotional Learning (SEL) | SRO/CSW |  | X | X | X | X | X | X | X | X | X | X |  |  |  | Guidance Manual, pages 7, 10-14, and 25-26
SSP FY23 Requirements & Guidance CSW Schools, pages 2-6
*SRO/CSW Activity logs | SRO/CSW |  | X | X | X | X | X | X | X | X | X | X |  |  |  | Guidance Manual, pages 7-8 and 39-42.
Officer performance assessment | Site Admin | [14 empty] | Guidance Manual, pages 8 & 43
Program Reporting info on mid/end of yr report? | SRO, CSW, Site Admin | [14 empty] | SSP FY23 Requirements & Guidance SRO JPO Schools, pages 3-4
SSP FY23 Requirements & Guidance CSW Schools, pages 3-4
Academic Screener | Site Admin or delegated staff
Behavioral Screener | SRO, CSW, Site Admin or delegated staff
Arizona Youth Risk Behavior Survey | SRO, CSW, Site Admin or delegated staff
Climate Surveys | SRO, CSW, Site Admin or delegated staff
Incident Data | Site Admin or delegated staff |  | X | X | X | X | X | X | X | X | X | X | X | X | X
Threat Assessment Training | SRO, CSW, Site Admin or delegated staff |  | X
Suicide Prevention Training | All School Staff |  | X
Other Supporting Documents:
Micro Training Videos:
SSP Training Registration
SSP Grant Requirement
School Safety Assessment and Prevention Team (SSAPT)
Role of the SRO/JPO
Role of the Counselor and Social Worker
Law Related Education as a Prevention Tool
Social Emotional Learning as a Prevention Tool

## Officer Checklist
Y/N | If Awarded an Officer
Required School Safety Program trainings are planned as appropriate:
o District Administrator
o Site Administrator (Principal or Principal Designee)
o Agency Supervisor
o Officer (SRO/JPO)
Introduction of the officer to staff, students, and general school community is scheduled by Site Administrator
School Safety Assessment and Prevention Team (SSAPT) meetings are scheduled by Site Administrator
Officer performance assessments are planned by Site administrator twice a year.
The operational calendar is periodically reviewed by the SSAPT
Agency Supervisor and Site Administrator are scheduled to meet at least once per semester.
Site Administrator is scheduled to review officer’s activity logs to determine progress made toward LRE instruction and monitor time off campus.
Collaboration between the officer and school personnel on school-wide safety and prevention is planned.
Officer is scheduled to implement Cohort LRE instruction according to requirements and needs identified by SSAPT’s review and assessment of data.
Officer is scheduled to implement Universal LRE instruction according to requirements and needs identified by SSAPT’s review and assessment of data.
Relationship building activities for officer, the community/school are discussed and planned by the Site Administrator, officer, and Agency Supervisor ie. Plan and participate in at least one or two events
Site Administrator, Agency Supervisor, and officer plan to be involved in site counsel/school committees as a way to build relationships with school staff
*Please note this is not an exhaustive list. For all program requirements, please refer to the School Safety Program Guidance Manual.

## CSW Checklist
Y/N | If Awarded a Counselor or Social Worker
Required School Safety Program trainings are planned as appropriate:
o District Administrator
o Site Administrator (Principal or Principal Designee)
o Counselor/Social Worker (CSW)
Introduction of the CSW to staff, students, and general school community is scheduled by Site Administrator
School Safety Assessment and Prevention Team (SSAPT) meetings are scheduled by Site Administrator
CSW performance assessments are planned by Site administrator twice a year.
The operational calendar is periodically reviewed by the SSAPT
District-level supervisor and Site Administrator are scheduled to meet at least once per semester.
Site Administrator is scheduled to review CSW's activity logs to determine progress made toward LRE instruction and monitor time off campus.
District and Site Administrator continually meet with CSW to ensure following professional models (American School Counselor Association [ASCA] and School Social Work Association of America [SSWAA])
Collaboration between the CSW and school personnel on school-wide safety and prevention is planned.
CSW is scheduled to implement Tier 1 interventions according to requirements and needs identified by SSAPT’s review and assessment of data.
CSW is scheduled to implement Tier 2 and 3 interventions according to requirements and needs identified by SSAPT’s review and assessment of data.
Relationship building activities for CSW the community/school are discussed and planned by the Site Administrator and CSW ie. Plan and participate in at least one or two events
District Administrator, Site Administrator, and CSW plan to be involved in site counsel/school committees as a way to build relationships with school staff
*Please note this is not an exhaustive list. For all program requirements, please refer to the School Safety Program Guidance Manual.